## Product Backlog
Product Name: | Library Database
Name: | Jerry Olds
Initials: | JO
Student ID: | 1001533643
Total Features | Left | Available | Completed | Sprint Ends
Start | 28 | 28 | 0
Sprint 1 | 24 | 28 | 4 | 2018-03-30
Sprint 2 | 19 | 28 | 9 | 2018-04-08
Sprint 3 | 19 | 28 | 9 | 2018-04-15
Sprint 4 | 10 | 28 | 18 | 2018-04-22
Sprint 5 | 10 | 28 | 18 | 2018-04-29
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Priority | Status | Expected Sprint | Actual Sprint # | As a … | I want to… | So that… | Type | Notes
CM | 1 | COM | 1 | 1 | PM | Create any type of media | I can check out media and create bundles | CLI | No Menu Required
BN | 2 | COM | 1 | 1 | PM | Create a bundle of media | I can check out bundles | CLI | No Menu Required
LB | 3 | COM | 1 | 1 | PM | Create a Librarian | They can check out/in media | CLI | No Menu Required
CUST | 4 | COM | 1 | 1 | LB | Create a Customer | We can keep track of who has what media | CLI | No Menu Required
CAT | 5 | COM | 2 | 2 | CU | Browse Catalog | they can see what is available | CLI | Need to list all media. Also list all bundles and media in those bundles. Creating Menu
AC | 6 | COM | 2 | 2 | PM | Add or Create | I can do it from a menu | CLI | Requires MVC
COMED | 7 | COM | 2 | 2 | LB | Check out Media | Customers can check out books | CLI | Librarian creates transaction with customer info
CIMED | 8 | COM | 2 | 2 | LB | Check in Media | Customers can check in books | CLI | Librarian modifies transaction to check in
PB | 9 | COM | 2 | 2 | CU | Pay Balance | Pay fine and check out new books | CLI | Customer can't check out media till balance is paid
SL | 10 | NS | 2 |  | PM | Save/Load Data | Don’t loose records of clients, media, and transaction | CLI | Should be options in the menu
GW | 11 | COM | 3 | 4 | ALL | Open a main GUI Window | I can use my mouse | GUI | Just opening a window
GMB | 12 | COM | 3 | 4 | PM | Create Media and Bundles Via GUI | Make this process more user friendly | GUI | Be able to do this in dialog windows
GCAT | 13 | COM | 3 | 4 | CU | Browse GUI Catalog | They can see what is available | GUI | Dialog Windows
GLIB | 14 | COM | 4 | 4 | PM | Create Librarians via GUI | They can check out/in media | GUI | Same as before but in a GUI
GCUST | 15 | COM | 4 | 4 | LB | Create Customers via aGUI | We can keep track of who has what media | GUI | Same as before but in a GUI
GOMED | 16 | COM | 4 | 4 | LB | Check out Media in GUI | Customers can check out books | GUI | Same as before but in a GUI
GIMED | 17 | COM | 4 | 4 | LB | Check in Media in GUI | Customers can check in books | GUI | Same as before but in a GUI
GBAL | 18 | COM | 4 | 4 | CU | Pay Balance in GUI | Pay fine and check out new books | GUI | Same as before but in a GUI
GMENU | 19 | COM | 4 | 4 | ALL | See a menu Bar | Make it easier to find stuff | GUI | Still have dialog boxes, but main menu dialog box is replaced with menu bar
CLIST | 20 | NS | 5 |  | PM | See everything that’s checked out and to who | See what's not in the library | GUI | A scrollable list
SL | 21 | NS | 5 |  | PM | Save/Load Data to default file name | Don’t loose records of clients, media, and transaction | GUI | Save to whatever file was opened, or a defualt name
LIBSL | 22 | NS | 5 |  | PM | Save and Load from different file names | Manage multiple libraries | GUI | Save/load to a user specified file
| 23 | NS | 6 |  | CU | See pictures of the media | So customers can see what book to look for | GUI | Picture must be added when creating media
| 24 | NS | 6 |  | ALL | Have users log in | So not all options are available to everyone | GUI | Can be hardcoded user names and passwords, such as "PM" for project manager with password "password". Each user type must have different usernames and passwords
| 25 | NS | 6 |  | LB | Bulk Check Out/In | So that librarians can check out multiple books at once | GUI | One window where multiple media ids can be typed, and check out multiple customers at once
| 26 | NS | 7 |  | ALL | Undo | Undo mistakes | GUI | Undo events (add media, check out, etc)
| 27 | NS | 7 |  | ALL | Copy Paste | Not waste time typing | GUI | Just do it where you can. It's built in some places. Don't start your own.
| 28 | NS | 7 |  | ALL | Have this in one window | It's not full of pop up dialog boxes | GUI | All contents in a window. Different window layout for different users

## Sprint 1
Sprint # | 1
Start on | 2018-03-24
End on | 2018-03-30
Total Tasks | 8
Day 1 Left | 8
Day 2 Left | 8
Day 3 Left | 8
Day 4 Left | 8
Day 5 Left | 8
Day 6 Left | 8
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | CM | Architecture | UML | JO | Add methods to Media and derived classes | COM
2 | CM | Media | Code | JO | Write and compile empty Media class | COM
3 | CM | Media | Code | JO | Variables and Constructor | COM
4 | CM | Media | Code | JO | Operator Overload << | NS - Not Started
5 | CM | Media | Test | JO | Test Constructor and << | NS - Not Started
6 | CM | Media | Code | JO | Add Get Methods | COM
7 | CM | Media | Test | JO | Test get methods in main | COM
8
Do the same for all other methods and classes
Should detail out all tasks done for completing this project
N | CM | Wrap Up | UML | Initials Here | Update UML to match new methods if changed | NS - Not Started
N + 1 | BN | Architecture | UML | Initials Here | Add methods to Bundle and derived classes | NS - Not Started
Follow Same pattern used in Media for Bundle and all other classes
Z | Demo | Wrap_Up | Delivery | Initials Here | Zip up and deliver sprint #1 (UML, Code, and spreadsheet) | NS - Not Started

## Sprint 2
Sprint # | 2
Start on | 2018-04-02
End on | 2018-04-08
Total Tasks | 0
Day 1 Left | 6
Day 2 Left | 6
Day 3 Left | 6
Day 4 Left | 6
Day 5 Left | 4
Day 6 Left | 2
Day 7 Left | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
VC | CAT | Architecture | Code | JO | Create Model View Controller | COM
CMED | AC | Media | Code | JO | Create Media | COM
PAY | PB | Financial | Code | JO | Pay balance | COM
SLF | SL | Media | Code | JO | Save/Load | IP- In Progress

## Sprint 3
Sprint # | 3
Start on | 2018-04-09
End on | 2018-04-15
Total Tasks | 3
Day 1 Left | 3
Day 2 Left | 3
Day 3 Left | 3
Day 4 Left | 3
Day 5 Left | 3
Day 6 Left | 3
Day 7 Left | 3
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
GUI-1 | GW | Architecture | Code | JO | Open a main GUI Window | IP- In Progress
GUI-2 | GMB | Architecture | Code | JO | Create Media and Bundles Via GUI | IP- In Progress
GUI-3 | GCAT | Architecture | Code | JO | Browse GUI Catalog | IP- In Progress

## Sprint 4
Sprint # | 4
Start on | 2018-04-16
End on | 2018-04-22
Total Tasks | 6
Day 1 Left | 6
Day 2 Left | 6
Day 3 Left | 6
Day 4 Left | 6
Day 5 Left | 4
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
4-1 | GLIB |  | Code | JO | Create Librarians via GUI | COM
4-2 | GCUST |  | Code | JO | Create Customers via aGUI | COM
4-3 | GOMED |  | Code | JO | Check out Media in GUI | COM
4-4 | GIMED |  | Code | JO | Check in Media in GUI | COM
4-5 | GBAL |  | Code | JO | Pay Balance in GUI | COM
4-6 | GMENU |  | Code | JO | See a menu Bar | COM

## Sprint 5
Sprint # | 5
Start on | 2018-04-23
End on | 2018-04-29
Total Tasks | 3
Day 1 Left | 3
Day 2 Left | 3
Day 3 Left | 3
Day 4 Left | 3
Day 5 Left | 2
Day 6 Left | 2
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
5-1 | CLIST |  | Code | JO | See what's not in the library | COM
5-2 | SL |  | Code | JO | Don’t loose records of clients, media, and transaction | COM
5-3 | LIBSL |  | Code | JO | Manage multiple libraries | COM